## Instructions
Use the Implementation Schedule Tab to document planning and implementation of the acticities proposed in your PCP.
Add rows as needed to document the required planning activities in your community.
In the detailed planning table: Developed a detailed planning schedule for your community to ensure you are ready to achieve all your required deadlines. Add rows (and columns) as needed as budget, hiring, planning, etc. needs will vary by community. Note which activities will occur in which fiscal year to ensure you meet your required targets.
To use this worksheet to estimate costs, enter the total cost for each activities through year 10 in column P. (or add a cost column per fiscal year if preferred)
Use the Inventory Structural BMPs tab to document existing, and planned structural BMPs in one central location.
Structural BMPs Permit Requirement: A schedule for implementation of all planned BMPs, including, as appropriate: obtaining funding, training, purchasing, construction, inspections, monitoring, operation and maintenance activities, and other assessment and evaluation components of implementation. Implementation of planned BMPs must begin upon completion of the Plan, and all non-structural BMPs shall be fully implemented within six years of the permit effective date. Structural BMPs shall be designed and constructed to ensure the permittee will comply with the 8, 10, 13, and 15 year phosphorus load milestones established in Table F-7 [of Appendix F of the MS4 Permit]. The plan shall be fully implemented as soon as possible, but no later than 15 years after the effective date of permit.
Non-structural BMPs note: In your schedule, you will need to consider how to fully implement non-structural BMPs by end of Permit Year 6 (June 30, 2024). Ensure in your schedule that your community has allocated adequate time to obtain additional funding, procure goods or services, and/or create new positions and hire additional staff, as appropriate, to successfully enhance street sweeping, catch basin cleaning, and/or leaf litter pickup. You will also need to consider how many structural BMPs you need (See Section 1.7.2) and the timing to complete design, permitting, bidding, and construction, as appropriate.

## ImplementationSchedule
PCP Element |  | Planning Activities | Permit Year (PY) 4 Fiscal Year (FY) 2022 | Permit Year (PY) 5 Fiscal Year (FY) 2023 | Permit Year (PY) 6 Fiscal Year (FY) 2024 | Permit Year (PY) 7 Fiscal Year (FY) 2025 | Permit Year (PY) 8 Fiscal Year (FY) 2026 | Permit Year (PY) 9 Fiscal Year (FY) 2027 | Permit Year (PY) 10 Fiscal Year (FY) 2028 | Permit Year (PY) 11 Fiscal Year (FY) 2029 | Permit Year (PY) 12 Fiscal Year (FY) 2030 | Permit Year (PY) 13 Fiscal Year (FY) 2031 | Permit Year (PY) 14 Fiscal Year (FY) 2032 | Permit Year (PY) 15 Fiscal Year (FY) 2033 | Municipal Cost
Overall |  | Enter Required Planning Activities
Written Phase I PCP |  | Planning: Complete Legal Analysis (due 6/30/2020), Funding Source Assessment (due 6/30/21), PCP Area (due 6/30/22), planned non-structural and structural controls, O&M Progarm, schedule for implementation (this table), estimated costs |  | Due June 30, 2023 | Review & report on activites annually
Fully Implement non-structural controls |  | See detailed planning table below |  | Start before June 30, 2023 | Due June 30, 2024
Performance Evaluation |  |  |  |  | Due June 30, 2024 | Due June 30, 2025 | Due June 30, 2026 | Due June 30, 2027 | Due June 30, 2028 | Due June 30, 2029 | Due June 30, 2030 | Due June 30, 2031 | Due June 30, 2032 | Due June 30, 2033
Planning Table: Use the rows below to developed a detailed planning schedule for your community to ensure you are ready to achieve all the deadlines demonstrated in the rows above. Add rows (and columns) as needed as budget, hiring, planning, etc. needs will vary by community. Note which activities will occur in which fiscal year to ensure you meet your required targets.
Non-structural BMPs | Type | Enter Required Planning Activities
Non-structural BMPs | Enhanced Street Sweeping | Planning: Budgeting, Secure Funding (capital requests, additional staff, consulting, etc.), Hiring, Purchasing/Outsourcing, Phased Roll-out, Training, etc. |  | Recommended launch | Due June 30, 2024
| Catch Basin Cleaning | Planning: Budgeting, Secure Funding (capital requests, additional staff, consulting, etc.), Hiring, Purchasing/Outsourcing, Phased Roll-out, Training, etc. |  | Recommended launch | Due June 30, 2024
| Enhanced Leaf Pickup Program | Planning: Budgeting, Secure Funding (capital requests, additional staff, consulting, etc.), Hiring, Purchasing/Outsourcing, Phased Roll-out, Training, etc. |  | Recommended launch | Due June 30, 2024
Structural BMPs | Location | Details | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr) | Total P-Reduction (lb/yr)
Year 8 Structural BMP target (Pexp ≤ Pallow + (PRR x 0.8)) | Address? Name? Project Reference? System type? | Including, as appropriate: obtaining funding, training, purchasing, construction, inspections, monitoring, operation and maintenance activities, and other assessment and evaluation components of implementation |  | Start before June 30, 2023 |  |  | 20% progress in reduction due June 30, 2026
| Add rows as needed, use inventory tab for individual project details |  |  | Start before June 30, 2023 |  |  | 20% progress in reduction due June 30, 2026
|  |  |  | Start before June 30, 2023 |  |  | 20% progress in reduction due June 30, 2026
Year 10 structural BMP target (Pexp ≤ Pallow + (PRR x 0.6)) | Address? Name? Project Reference? | Including, as appropriate: obtaining funding, training, purchasing, construction, inspections, monitoring, operation and maintenance activities, and other assessment and evaluation components of implementation |  | Start before June 30, 2023 |  |  |  |  | 40% progress in reduction due June 30, 2028
| Add rows as needed, use inventory tab for individual project details |  |  | Start before June 30, 2023 |  |  |  |  | 40% progress in reduction due June 30, 2028
|  |  |  | Start before June 30, 2023 |  |  |  |  | 40% progress in reduction due June 30, 2028
|  |  |  | Start before June 30, 2023 |  |  |  |  | 40% progress in reduction due June 30, 2028
Year 13 structural BMP target (Pexp ≤ Pallow + (PRR x 0.3)) | Address? Name? Project Reference? | Including, as appropriate: obtaining funding, training, purchasing, construction, inspections, monitoring, operation and maintenance activities, and other assessment and evaluation components of implementation |  | Start before June 30, 2023 | [7 empty] | 70% progress in reduction due June 30, 2031
| Add rows as needed, use inventory tab for individual project details |  |  | Start before June 30, 2023 | [7 empty] | 70% progress in reduction due June 30, 2031
|  |  |  | Start before June 30, 2023 | [7 empty] | 70% progress in reduction due June 30, 2031
|  |  |  | Start before June 30, 2023 | [7 empty] | 70% progress in reduction due June 30, 2031
Year 15 structural BMP target (Pexp ≤ Pallow) | Address? Name? Project Reference? | Including, as appropriate: obtaining funding, training, purchasing, construction, inspections, monitoring, operation and maintenance activities, and other assessment and evaluation components of implementation |  | Start before June 30, 2023 | [9 empty] | Due June 30, 2033
| Add rows as needed, use inventory tab for individual project details |  |  | Start before June 30, 2023 | [9 empty] | Due June 30, 2033
|  |  |  | Start before June 30, 2023 | [9 empty] | Due June 30, 2033
|  |  |  | Start before June 30, 2023 | [9 empty] | Due June 30, 2033
Note on L5: 20% of Stormwater Phosphorus Load Reduction Requirement must be achieved
Note on N5: 25% of Stormwater Phosphorus Load Reduction Requirement must be achieved
Note on C8: Julie: Sarah, can you make 3 rows for each entry, 1. for Budgeting & securing funding, 2. Hiring & Training, 3. Equipment purchases

## InventoryStructuralBMPs
Project Name | Location | Date of Installation | Current Structural BMP Type | Design Volume (ft3) | Total Acres Managed | Total Annual P-Reduction (lb/yr) | Cost ($) | Add columns as needed | Party Responsible for Maintenance | Date of Last Maintenance